## Remediation Tracker
Finding ID | Severity | Security Area | Vulnerability / Finding | Risk / Impact | Recommended Fix | Priority | File Name | Task / Section | Status | Owner | Target Date | Testing Result | Production Sign-off
1 | Critical | Secret Management | Azure access token registered with no_log: false | Azure token may appear in AAP/AWX job logs or callbacks | Set no_log: true on token retrieval and all downstream secret-handling tasks | P0 |  |  | Open
2 | Critical | Secret Management | Key Vault response registered with no_log: false | AD credentials retrieved from Key Vault may be exposed in logs | Set no_log: true; never print the response body | P0 |  |  | Open
3 | Critical | Secret Management | AD password stored as an Ansible fact | Password remains in automation memory/facts longer than necessary | Minimize secret lifetime; prefer AAP credential/Key Vault integration where possible | P0 |  |  | Open
4 | Critical | WinRM | WinRM uses HTTP / port 5985 | Management communication has weaker protection and increased interception/credential-relay exposure | Move to WinRM HTTPS and preferably Kerberos where supported | P0 |  |  | Open
5 | Critical | WinRM | ansible_winrm_server_cert_validation: ignore | Windows server identity is not validated; increases MITM risk | Use trusted certificates and server_cert_validation: validate | P0 |  |  | Open
6 | Critical | Authentication | WinRM uses NTLM | NTLM increases credential-relay/lateral-movement risk | Prefer Kerberos with HTTPS and appropriate AD configuration | P0 |  |  | Open
7 | Critical | AD Privileges | Automation service account may have excessive AD privileges | Compromise could enable major AD compromise | Delegate only required permissions; never use Domain Admin unnecessarily | P0 |  |  | Open
8 | Critical | GPO | Direct modification of GptTmpl.inf | Can corrupt GPO/SYSVOL and bypass supported management mechanisms | Use supported Group Policy APIs/cmdlets/modules | P0 |  |  | Open
9 | Critical | GPO | Direct modification of GPT.INI | Incorrect versioning can cause GPO replication/application problems | Let supported GPO mechanisms manage policy versions | P0 |  |  | Open
10 | Critical | Privilege Escalation | GPO adds opsintel to local Administrators | Compromise of account can provide admin access to managed servers | Use controlled AD security groups/PAM/JIT instead of direct user assignment | P0 |  |  | Open
11 | Critical | Authorization | requester_confirmation=YES is treated as approval | User may potentially approve their own AD change | Implement AAP workflow approval and ITSM/change approval | P0 |  |  | Open
12 | High | Input Validation | User-controlled values inserted into PowerShell | Malicious input could alter PowerShell/LDAP operations | Use strict allow-list validation and safe PowerShell parameter handling | P1 |  |  | Open
13 | High | AD Object Handling | Server name repeatedly used as object identity | Names can change or be ambiguous, risking wrong-object operations | Resolve ObjectGUID/DN once and use immutable identity | P1 |  |  | Open
14 | High | Concurrency | Check-then-create operations can race | Concurrent AWX jobs may create/modify the same object | Add concurrency controls/locking and robust idempotency | P1 |  |  | Open
15 | High | Error Handling | Key Vault retrieval uses ignore_errors: yes | Credential retrieval failure may not immediately stop execution | Hard-stop on credential retrieval failure | P1 |  |  | Open
16 | High | Logging | Azure HTTP response may be printed | Authentication/Key Vault errors may expose infrastructure details | Log status/correlation ID only; never full response bodies | P1 |  |  | Open
17 | High | Error Handling | Rescue block provides only generic failure message | Root cause may be difficult to audit/troubleshoot | Capture structured error information without exposing secrets | P1 |  |  | Open
18 | High | GPO / Policy Refresh | GPUpdate failure is ignored | Job may report success while policy is not applied | Distinguish configuration success from policy propagation failure | P1 |  |  | Open
19 | High | GPO Ownership | Existing GPO trusted based only on name | Automation could modify an unrelated/manual GPO with same name | Validate GPO GUID/metadata/owner before modifying | P1 |  |  | Open
20 | High | GPO Naming | GPO names can collide | Existing unrelated GPO could be modified | Use deterministic unique naming and ownership metadata | P1 |  |  | Open
21 | Medium | Dry Run | Dry-run mainly skips changes | Does not provide a complete preview of intended modifications | Build true change-preview/diff mode | P2 |  |  | Open
22 | Medium | Audit | Operation ID alone is insufficient | Difficult to correlate request, approval, AWX job and AD changes | Record requester, approver, job ID, ticket, server, GPO GUID and timestamp | P2 |  |  | Open
23 | Medium | Change Management | No strong change-ticket validation | AD changes may occur without traceable approved change | Require and validate ITSM change/request ID | P2 |  |  | Open
24 | Medium | Azure Identity | Long-lived Azure client secret architecture | Compromise of client secret could provide Key Vault access | Move toward Managed Identity/Workload Identity where supported | P2 |  |  | Open
25 | Good | TLS | Azure validate_certs: yes | Azure TLS certificates are validated | Keep enabled; never disable certificate validation | Maintain |  |  | Implemented
26 | Good | Dependencies | Ansible collection versions are pinned | Improves reproducibility and prevents unexpected upgrades | Maintain version control and periodically patch versions | Maintain |  |  | Implemented
27 | Good | Safety | Explicit requester confirmation exists | Provides a basic execution safeguard | Keep but supplement with real approval workflow | Maintain |  |  | Implemented
28 | Good | AD Validation | Server existence validation is performed before modification | Reduces accidental changes to nonexistent/wrong servers | Keep and strengthen with ObjectGUID/DN validation | Maintain |  |  | Implemented
29 | Good | Privilege Model | Design intends to avoid Domain Admin | Correct architectural direction | Continue toward narrowly delegated service account | Maintain |  |  | Implemented

## Summary
Metric | Value
Total Findings | 29
Critical Findings | 11
High Findings | 9
Medium Findings | 4
Good / Existing Controls | 5
P0 Findings | 11
P1 Findings | 9
P2 Findings | 4
Open / In Progress
Fixed / Validated
Production Sign-offs Approved

## Remediation Guidance
Priority | Meaning | Recommended Action
P0 | Critical security issue | Fix before production deployment; security validation required
P1 | High-risk issue | Fix before production unless formally risk-accepted
P2 | Medium-risk improvement | Fix before or shortly after production based on risk assessment
Maintain | Existing good control | Keep control and periodically validate